## Summary
Device Supplier Conformance — Coverage & Gap Plan
Source | github.com/margo/conformance_documentation — device_supplier_conf_requirements.md
Updated | 2026-08-31 — adds, per requirement, plain-language 'what's needed to cover it' plus whether it needs a scripted deployment, a real Compose deploy, or a real Helm/K8s deploy. Verdicts read from the live suite + mock server (device-supplier/cmd/device-supplier/main.go, testcases/user2Device, testcases/device-core).
Status | Count
Next Stage | 28
Covered | 11
Covered (Indirect) | 6
Covered (suite self-test) | 6
Partial | 5
Covered (suite self-test) — you had marked Advisory | 2
MIAF Override User defined behavior hence we cannot test | 2
Need to create a test | 2
Blocked (library) — htmsig has rsa-pss-sha512 only, not rsa-pss-sha256 | 1
Covered (suite self-test) — MIAF may still supersede | 1
Need to create a test Add new tests | 1
Not testable | 1
Not yet implemented | 1
Partly covered (suite self-test) — abort half done; 'preserve previous state' pending | 1
Partly covered (suite self-test) — abort half done; 'retain previous state' pending | 1
Rollback not yet implemented | 1
TOTAL | 70
[2026-09-02] WP-1 + WP-2 shipped: MI-004, MI-012, MI-014, MI-018 now covered via the device-conformance self-test group (79/79). MI-013 (rsa-pss-sha256) is blocked by the htmsig library (rsa-pss-sha512 only). New certs added to generate-certs.sh; mock gained certRFC5280Violation() + a :3002 non-CA TLS listener; runner gained signing_key/signing_algorithm and verify_tls/expect_transport_error.

## Coverage
CR-ID | Section | Strength | Requirement | Coverage Status | Current Evidence | Remarks | Scripted deployment needed | Real Compose/Helm/k8s deploy needed | Real Helm / K8s deploy needed | Other prerequisites | Effort
MARGO-DEV-MANAGEMENTINTERFACE-001 | Management Interface | MAY | Additional signature algorithms MAY be supported. | MIAF Override User defined behavior hence we cannot test | — | Do we need to cover it — it is an optional permission, not a requirement. | No | No | No | — | None
MARGO-DEV-MANAGEMENTINTERFACE-002 | Management Interface | MAY | Clients MAY choose any of the required algorithms that fits their hardware capabilities. | MIAF Override User defined behavior hence we cannot test | — | Do we need to cover it — optional client choice. | No | No | No | — | None
MARGO-DEV-MANAGEMENTINTERFACE-003 | Management Interface | MAY | The Certificate API MAY be used to retrieve the root CA over an already trusted channel. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-004 | Management Interface | MUST | All client certificates MUST conform to RFC 5280 standards. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 79/79 steps pass | [2026-09-02] WP-2 DONE. Mock now runs certRFC5280Violation() on onboarding (validity window, empty-subject/no-SAN, RSA<2048 / EC<P-256) -> 422. Positive: normal device cert still onboards. Negative: device-weakkey-cert.pem (RSA-1024) rejected. Verified: negative control (good cert) still 201. (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Add a check that actually opens the device certificate and confirms the RFC 5280 basics (X.509 v3, valid dates, subject, SubjectAltName, keyUsage). Plus one negative test: onboard with a deliberately broken cert and expect it to be rejected.) | No | No | No | New 'valid X.509' assertion in the runner; a few hand-made bad certs; the mock WFM must actually reject a non-conforming cert. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-005 | Management Interface | MUST | Both the WFM and Device client MUST utilize X.509 certificates to represent themselves within API interactions. | Covered (Indirect) | every signed interaction uses the X.509 client cert | Already covered indirectly. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-006 | Management Interface | MUST | Clients MUST verify computed digests match manifest values; any mismatch MUST abort update and preserve previous state. | Partly covered (suite self-test) — abort half done; 'preserve previous state' pending | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: fixture 'bundle_digest_mismatch' + evaluateManifest downloads the artifact, sha256s it, flags the mismatch (abort-on-mismatch proven). The 'preserve previous state' half still needs a running deployment (WP-4) or MIAF. Your 'Update and Rollback feature not yet supported' note kept for that half. (prior status: "Update and Rollback feature not yet supported" — prior remark: We need a real device-agent that actually applies desired state. Then use the mock's test-control to hand it a manifest whose bundle digest is wrong, and check the agent refuses the update and keeps the deployment that was already running.) | Single-app (mock test-control) | abort half: No · preserve-state half: Yes | No | Reference device-agent under test; a 'serve wrong bundle digest' switch on the mock. | Small done / rest = WP-4 or MIAF
MARGO-DEV-MANAGEMENTINTERFACE-007 | Management Interface | MUST | For every change in deployment state, the client MUST report the corresponding status to the WFM using the Deployment Status API. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-008 | Management Interface | MUST | If a manifest references an unsupported digest algorithm, the client MUST treat the manifest as invalid and abort processing. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: mock fixture 'unsupported_digest_algorithm' rewrites every manifest digest to sha512; runner rule evaluateManifest (sha256-only) + expect_manifest_rejected flags it. Fully covers the requirement. (prior status: "Need to create a test" — prior remark: Reference agent + a mock switch that emits a manifest referencing a non-sha256 algorithm (sha512:/md5:). Assert the agent throws out the whole manifest.) | Single-app (mock test-control) | No | No | Reference device-agent; 'bad digest algorithm' switch on the mock. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-009 | Management Interface | MUST | If any digest validation fails, the client MUST abort the update and retain the previous state. | Partly covered (suite self-test) — abort half done; 'retain previous state' pending | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: companion to MI-006, same fixture/rule. Abort-on-any-digest-failure proven; retain-previous-state half needs a running deployment (WP-4) or MIAF. MIAF-override note kept for that half. (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Companion to MI-006 — same setup and reference agent; assert that after the failed update nothing changed on disk or in the running set.) | Single-app (mock test-control) | abort half: No · retain-state half: Yes | No | Reference device-agent; digest fault-injection on the mock. | Small done / rest = WP-4 or MIAF
MARGO-DEV-MANAGEMENTINTERFACE-010 | Management Interface | MUST | If manifestVersion is not strictly greater than stored, the update MUST be rejected. | Covered (suite self-test) — MIAF may still supersede | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: fixture 'non_increasing_manifest_version' forces manifestVersion back to 1 after the runner has recorded a higher one; evaluateManifest + _seenManifestVersion tracking flags the rollback. Covers 'update MUST be rejected'. Kept your MIAF-override note in case MIAF changes the approach. (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Reference agent that remembers the last accepted manifestVersion. Drive the mock: give version 3, let it apply, then give version 2 and assert the agent rejects the rollback.) | Single-app, evolving (mock test-control) | No | No | Reference device-agent with persisted version; a 'set explicit / lower manifestVersion' knob on the mock. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-011 | Management Interface | MUST | Implementations MUST support allowable signature algorithm: ecdsa-p256-sha256. | Covered (Indirect) | every signed request uses ecdsa-p256-sha256 | Already covered indirectly. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-012 | Management Interface | MUST | Implementations MUST support allowable signature algorithm: ecdsa-p384-sha384. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 79/79 steps pass | [2026-09-02] WP-1 DONE. New certs/device-ec384-{key,cert}.pem; runner signs per scenario signing_key; htmsig derives ecdsa-p384-sha384 from the P-384 curve. Signed GET succeeds (mock verifies P-384). Negative control: p384 cert + p256 key -> 401. (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Add a P-384 signing path to the test client plus a P-384 device certificate, onboard with it, make one signed request and expect success. Confirm the mock's verifier accepts P-384.) | No | No | No | New signer path + EC P-384 cert; check the mock verifier accepts it. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-013 | Management Interface | MUST | Implementations MUST support allowable signature algorithm: rsa-pss-sha256. | Blocked (library) — htmsig has rsa-pss-sha512 only, not rsa-pss-sha256 | testcases/device-conformance/test-scenarios.json · group device-conformance · 79/79 steps pass | [2026-09-02] WP-1: cannot cover with the current signing library (github.com/lestrrat-go/htmsig v1.0.0 implements rsa-pss-SHA512, not the rsa-pss-SHA256 Margo requires). Needs a library patch/fork or a second signing lib. Certs are ready (reuse device-rsa2048). Everything else (runner signing_algorithm plumbing) is in place. (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Same pattern as MI-012 with an RSA-2048 key and an rsa-pss-sha256 signing path.) | No | No | No | New signer path + RSA cert; check the mock verifier accepts it. | Medium — blocked on library
MARGO-DEV-MANAGEMENTINTERFACE-014 | Management Interface | MUST | Implementations MUST support allowable signature algorithm: rsa-v1_5-sha256. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 79/79 steps pass | [2026-09-02] WP-1 DONE. certs/device-rsa2048-{key,cert}.pem; scenario pins signing_algorithm=rsa-v1_5-sha256 (htmsig would default RSA keys to rsa-pss-sha512). Signed GET succeeds (mock verifies rsa-v1_5-sha256). (prior status: "MIAF Override. Once MIAF is implemented this scrnario will be overridden by MIAF" — prior remark: Add an rsa-v1_5-sha256 signing path; can reuse the RSA cert from MI-013.) | No | No | No | New signer path (RSA plumbing shared with MI-013). | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-015 | Management Interface | MUST | Once reconciliation succeeds, the client MUST durably persist the new manifestVersion and associated ETag. | Need to create a test Add new tests | ETag round-trips work; persistence does not exist in the driver | Reference agent that writes the accepted manifestVersion + ETag to durable storage. After a successful reconcile, read that storage back and confirm the values were saved. | Single-app (evolving) | Single-app (evolving) scripted | No | Reference device-agent with persistent state. | Large
MARGO-DEV-MANAGEMENTINTERFACE-016 | Management Interface | MUST | The Device supplier, via its WFM Client, MUST implement the client side of the API specification contract. | Covered (Indirect) | full client surface exercised end-to-end | Already covered indirectly (mirror of WFM MI-023). | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-017 | Management Interface | MUST | The client MUST persist both the last accepted manifestVersion and ETag to prevent rollback across restarts. | Rollback not yet implemented | — | As MI-015, then stop and restart the agent, feed it the earlier (lower) manifestVersion and confirm it is not re-applied. | Single-app (evolving) | Single-app (evolving) | No | Reference device-agent you can restart under test. | Large
MARGO-DEV-MANAGEMENTINTERFACE-018 | Management Interface | MUST | The client MUST trust the WFM's server certificate through a pre-provisioned or securely obtained root CA. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 79/79 steps pass | [2026-09-02] WP-2 DONE. Runner 'verify_tls' verifies the server cert against certs/ca-cert.pem; 'expect_transport_error' passes on a refused connection. Positive: real WFM (CA-signed) trusted. Negative: mock's new :3002 listener serves a non-CA cert -> connection refused. Negative control confirmed. (prior status: "Partial" — prior remark: Make the test client actually verify the TLS server certificate against the root CA it fetched (today it likely skips verification). Then a negative test: run a second mock whose server cert is from a different CA and confirm the client refuses to connect.) | No | No | No | TLS trust enforcement in the test client; a second, untrusted server cert. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-019 | Management Interface | MUST | The client MUST verify the digest of every fetched artifact before use. | Covered (suite self-test) | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: fixture 'deployment_digest_mismatch' corrupts one deployments[].digest (bundle digest left valid); evaluateManifest fetches+hashes every ref via eachManifestRef and flags the per-deployment mismatch. Single-app is enough (one deployment, index 0). Matches your 'match the bundle digest / sha256' note. (prior status: "Need to create a test and match the bundle digest sha256" — prior remark: Reference agent + a multi-deployment manifest. Corrupt ONE deployment YAML's digest on the mock and assert the agent rejects the update, not just that one file.) | Single-app (mock test-control) | No | No | Reference device-agent; per-artifact fault injection on the mock. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-020 | Management Interface | MUST | The device management client MUST Base64-encode the digest and include it in the Content-Digest header. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-021 | Management Interface | MUST | The device management client MUST create a Signature Base String including @method, @target-uri, and Content-Digest. | Covered (Indirect) | all signed requests | Already covered indirectly. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-022 | Management Interface | MUST | The device management client MUST generate a SHA256 digest of the HTTP request body. | Covered (Indirect) | Content-Digest scenarios | Already covered indirectly. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-023 | Management Interface | MUST | The device management client MUST generate the Signature header by signing the Signature Base String using the client's X.509 private key. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-024 | Management Interface | MUST | The device management client MUST insert Content-Digest, Signature-Input, and Signature headers in the HTTP/1.1 request. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-MANAGEMENTINTERFACE-025 | Management Interface | MUST NOT | bundle.sizeBytes MUST NOT be used for integrity verification. | Covered (suite self-test) — you had marked Advisory | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED despite the Advisory call: fixture 'wrong_size_bytes' sets sizeBytes=1 with digests intact; scenario asserts expect_manifest_accepted, proving the suite does NOT treat a sizeBytes difference as an integrity failure. Cheap (shares the wrong_size_bytes fixture with MI-026). Revert to Advisory if you prefer. (prior status: "No test needed Advisory" — prior remark: Reference agent. Mock serves a manifest where bundle.sizeBytes is wrong but the digest is right — assert the agent still accepts it (proves it is not gating on size). Companion: size right, digest wrong — assert reject.) | Single-app (mock test-control) | No | No | Reference device-agent; 'wrong sizeBytes' knob on the mock. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-026 | Management Interface | MUST NOT | deployments[].sizeBytes MUST NOT be used for integrity verification. | Covered (suite self-test) — you had marked Advisory | testcases/device-conformance/test-scenarios.json · group device-conformance · 71/71 steps pass | [2026-09-02] SELF-TEST ADDED: same 'wrong_size_bytes' fixture (it also rewrites deployments[].sizeBytes); same expect_manifest_accepted assertion. No extra code beyond MI-025. (prior status: "No test needed Advisory" — prior remark: Same as MI-025 but at the per-deployment level; multi-deployment manifest makes it clearer.) | Single-app (mock test-control) | No | No | Reference device-agent; 'wrong sizeBytes' knob on the mock. | Small (done)
MARGO-DEV-MANAGEMENTINTERFACE-027 | Management Interface | PREFERRED | Running the device's management client as containerized services is preferred (not required). | Not testable | — | Nothing to do — non-normative preference. | No | No | No | — | None
MARGO-DEV-MANAGEMENTINTERFACE-028 | Management Interface | SHOULD | If manifestVersion is not strictly greater, the event SHOULD be logged as a security event (logging specifics TBD). | Not yet implemented | — | Reference agent that emits security logs. Trigger a rollback attempt (see MI-010) and check the agent's log for the security event. Also partly blocked by the spec itself ('logging specifics TBD'). | Single-app (evolving) | Single-app (evolving) scripted | No | Reference device-agent with log output; spec detail to firm up. | Large
MARGO-DEV-DEPLOYMENT-001 | Deployment | MUST | A device MUST support onboarding and management from only a single workload fleet manager. | Partial | onboarding tested; no second-WFM rejection | Reference agent that records which WFM it belongs to. After onboarding to WFM A, point a second WFM (or a second mock instance) at it and confirm the agent refuses to be managed by two. | No | No | No | Reference device-agent; a second WFM instance. | Large
MARGO-DEV-DEPLOYMENT-002 | Deployment | MUST | All current device roles MUST meet the listed requirements to be considered Margo compliant. | Covered |  | Already covered. | No | No | No | — | Done
MARGO-DEV-DEPLOYMENT-003 | Deployment | MUST | All devices MUST provide a workload fleet management client. | Covered (Indirect) | onboarding + deployment flows throughout | Already covered indirectly. | No | No | No | — | Done
MARGO-DEV-DEPLOYMENT-004 | Deployment | MUST | All devices MUST provide an OCI container runtime. | Covered | step-core-1.1/1.2 (supportedRuntimes=["oci"]) | Covered as a capability declaration. Stronger proof would actually pull and run an OCI image (see WP-4). | No | No | No | — | Done (capability)
MARGO-DEV-DEPLOYMENT-005 | Deployment | MUST | All devices MUST provide an OTEL collector. | Covered | step-core-1.1/1.2 (otelCollector=true) | Covered as a capability declaration. Real proof is the Observability section, which is not implemented. | No | No | No | — | Done (capability)
MARGO-DEV-DEPLOYMENT-006 | Deployment | MUST | Devices filling the standalone cluster role MUST provide a Kubernetes orchestration platform. | Partial | helm role declared (step-core-1.2); no real K8s | Run the suite on a real cluster-role device with a Kubernetes cluster, deploy a Helm chart through the normal flow, and confirm it lands as running workloads. | Single-app (Helm) | Yes, Single-app (Helm) | Yes | Real Kubernetes test environment + a cluster-role device. | Large
MARGO-DEV-DEPLOYMENT-007 | Deployment | MUST | Devices filling the standalone cluster role MUST provide capabilities for deploying Helm charts. | Covered | step-core-1.2 (capability declared + accepted) | Covered as a capability. Stronger proof = a real helm install (shares work with DEP-006 / AD-005). | No | No | No | — | Done (capability)
MARGO-DEV-DEPLOYMENT-008 | Deployment | MUST | Devices filling the standalone device role MUST provide Compose-compliant software as the orchestration platform. | Covered | step-core-1.1 (capability declared + accepted) | Covered as a capability. Stronger proof = a real `docker compose up` of a sample app (WP-4). | No | No | No | — | Done (capability)
MARGO-DEV-DEPLOYMENT-009 | Deployment | MUST | Devices filling the standalone device role MUST provide capabilities for deploying Compose applications. | Covered | step-core-1.1 (capability declared + accepted) | Covered as a capability. Stronger proof = a real Compose deployment of a sample app (WP-4). | No | No | No | — | Done (capability)
MARGO-DEV-APPLICATIONDESCRIPTION-001 | Application Description | MUST | After deployment, the device MUST provide the specified amount of memory for the application. | Partial | reported memory capability is validated (step-2.x, step-core-1.x) | Deploy a real sample app that requests a specific memory amount, on a real device running Docker Compose, then inspect the container (docker inspect / cgroup limits) and confirm the memory is actually there. Today we only check that the device *reported* enough memory. | Single-app | Yes for cluster role(Single-app) |  | Real device + runtime; a sample Margo app whose Application Description sets resources; a container-inspection step. | Large
MARGO-DEV-APPLICATIONDESCRIPTION-002 | Application Description | MUST | After deployment, the device MUST provide the specified amount of storage for the application. | Partial | reported storage capability validated | Same as AD-001 but inspect the volume / disk allocation after deploy. | Single-app | Yes for cluster role(Single-app) |  | Real device + runtime; sample app; volume-inspection step. | Large
MARGO-DEV-APPLICATIONDESCRIPTION-003 | Application Description | MUST | After deployment, the device MUST provide the specified number of CPU cores for the application. | Partial | reported CPU capability validated | Same as AD-001 but inspect the CPU limit (cgroup cpu quota) after deploy. | Single-app | Yes for cluster role(Single-app) |  | Real device + runtime; sample app; cpu-inspection step. | Large
MARGO-DEV-APPLICATIONDESCRIPTION-004 | Application Description | MUST | If compose component wait is True, the device MUST wait until the compose file has finished starting before starting the next. | Need to create a test | no runtime harness | With a real Compose runtime: deploy a multi-component Compose app with wait=true and confirm component N+1 only starts after component N is healthy (compare container start timestamps / health status). | Multi-app | Yes(Multi-app) | No | Real Compose runtime; a multi-component sample app; timing/health observation. | Large
MARGO-DEV-APPLICATIONDESCRIPTION-005 | Application Description | MUST | If helm component wait is True, the device MUST wait for helm chart to finish installing before installing the next. | Need to create a test | no runtime harness | Same as AD-004 but with Helm: a multi-chart release with wait=true, confirm ordered install. | Multi-app | Yes(Multi-app) |  | Real Helm/K8s runtime; multi-chart sample; ordered-install observation. | Large
MARGO-DEV-OBSERVABILITY-001 | Observability | MAY | For multi-node clusters the device owner MAY use the DaemonSet deployment model. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-002 | Observability | MAY | The device owner MAY choose the deployment model but MUST use one of the specified approaches. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-003 | Observability | MAY | The device owner MAY deploy multiple OpenTelemetry collectors as long as all required observability data is collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-004 | Observability | MUST | Cluster (single or multi-node) observability data MUST be collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-005 | Observability | MUST | Cluster events observability data MUST be collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-006 | Observability | MUST | End users MUST be able to export observability data from a device or cluster to collectors/backends. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-007 | Observability | MUST | For Docker/Podman devices, container observability data MUST be collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-008 | Observability | MUST | For Kubernetes devices, the minimum list of observability data MUST be provided. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-009 | Observability | MUST | For multi-node clusters the device owner MUST ensure cross-node communication between workloads and collectors is secure. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-010 | Observability | MUST | For standalone and clustered devices there MUST be at least one OpenTelemetry collector deployed. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-011 | Observability | MUST | Host observability data MUST be collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-012 | Observability | MUST | If Docker Stats Receiver/Podman Stats Receiver is not used, the device owner MUST provide the same output as default. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-013 | Observability | MUST | If Host Metrics Receiver is not used, the device owner MUST provide the same output as default configuration. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-014 | Observability | MUST | If Kubelet Stats Receiver is not used, the device owner MUST provide the same output as its default configuration. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-015 | Observability | MUST | If Kubernetes Attributes Processor is not used, the device owner MUST provide the same metadata as its default configuration. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-016 | Observability | MUST | If Kubernetes Cluster Receiver is not used, the device owner MUST provide the same output as its default configuration. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-017 | Observability | MUST | If Kubernetes Objects/Events Receiver is not used, the device owner MUST provide the same output as the default configuration. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-018 | Observability | MUST | If OTLP Receiver is not used, the device owner MUST provide the same functionality as the OTLP Receiver. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-019 | Observability | MUST | If the Workload Fleet Management Client is not containerized, the device owner MUST ensure its resource usage observability data is available from the collector. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-020 | Observability | MUST | Metadata identifying the observability data source MUST be added to received observability data. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-021 | Observability | MUST | Node, Pod and Container observability data MUST be collected. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-022 | Observability | MUST | The collector MUST receive data using the OTLP format. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-023 | Observability | MUST | The device owner MUST deploy and configure an OpenTelemetry collector on their device. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-024 | Observability | MUST NOT | The device owner MUST NOT attempt to inject auto-instrumentation into compliant workloads not owned by the device owner. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-025 | Observability | MUST NOT | The device owner MUST NOT pre-configure exporters to send observability data from the device. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-026 | Observability | MUST NOT | The device owner MUST NOT require the use of the sidecar deployment model at this time. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-027 | Observability | NOT REQUIRED | Device owners are NOT required to provide backends for consuming observability data on their devices. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred
MARGO-DEV-OBSERVABILITY-028 | Observability | RECOMMENDED | It is recommended the Workload Fleet Management Client be deployed as a containerized workload. | Next Stage | — | Observability testing is not implemented and is deferred. Closing it needs a real OTEL collector running on a device plus inspection of the telemetry it emits — a separate test mechanism, tracked as its own effort (WP-6). | No | No | No | Dedicated observability harness (deferred). | Deferred

## Gap Plan
Work package | Requirements it closes | Needs a deployment? | Needs Compose? | Needs Helm/K8s? | Other prerequisites | Effort | Plain-words summary
WP-1 Extra signature algorithms | MI-012, MI-014 — DONE. MI-013 blocked by signing library (htmsig: rsa-pss-sha512 only). | No | No | No | P-384 EC cert + RSA-2048 cert; new signer paths in the test client; confirm the mock verifier accepts them | Done (MI-013 needs a library patch) | The spec requires the device client to support four signing algorithms; today it only does ecdsa-p256. Add the other three signing paths + matching certs, then one signed request per algorithm expecting success.
WP-2 Certificate & TLS trust | MI-004, MI-018 — DONE. | No | No | No | New 'valid X.509' assertion operator; a few malformed certs; make the test client enforce TLS verification against the fetched root CA; a second server cert from an untrusted CA | Done | Prove certs are RFC 5280-shaped and prove the client actually refuses a WFM whose server cert is not signed by the trusted root CA.
WP-3 Reference device-agent under test | MI-015, MI-017, MI-028, DEPLOYMENT-001; plus the 'preserve/retain previous state' halves of MI-006 & MI-009. (MI-008, MI-010, MI-019 fully — and MI-025/026 — are already closed by the lighter self-test path, no reference agent needed.) | Yes — mostly single-app scripted state; multi-app for MI-019/MI-026; evolving for MI-010/015/017/028 | Only MI-006 / MI-009 (need a running deployment to show 'previous state kept') | No | A real reconciling device-agent the harness can start/stop/inspect; fault-injection knobs on the mock WFM test-control: wrong bundle digest, wrong per-deployment digest, non-sha256 algorithm, explicit/lower manifestVersion, wrong sizeBytes | Large (structural) | Only the requirements that genuinely need persistent client state / logs / multi-WFM memory remain here. Digest-algorithm, digest-mismatch and version-rollback checks turned out to be doable with a mock fixture + a runner rule, already shipped.
WP-4 Real Compose runtime harness | AD-001, AD-002, AD-003, AD-004; strengthens DEPLOYMENT-008 / DEPLOYMENT-009 | Single-app for AD-001/002/003; multi-component for AD-004 | Yes | No | A real device running Docker Compose; sample Margo apps that declare memory/storage/cpu and (for AD-004) multiple components with wait=true; post-deploy container-inspection steps (docker inspect / cgroups) | Large | 'After deployment the device provides the specified memory/storage/CPU' can only be proven by actually deploying an app and inspecting the container limits. AD-004 additionally checks components start in order.
WP-5 Real Helm / Kubernetes runtime harness | AD-005, DEPLOYMENT-006; strengthens DEPLOYMENT-007 | Single-app (Helm) for DEP-006; multi-chart for AD-005 | No | Yes | A cluster-role device with a real Kubernetes cluster; sample Helm charts; post-install inspection | Large | The cluster-role requirements need a real K8s platform and a real helm install to verify, not just a declared capability.
WP-6 Observability (deferred) | All 28 MARGO-DEV-OBSERVABILITY-* | No | No | Possibly | A dedicated observability test harness: deploy an OTEL collector on a device and inspect emitted telemetry | Deferred | Not implemented. Separate mechanism from API conformance; parked for now.